## Sheet1
Job Desk
Task | Tanggal Mulai | Tanggal Selesai | Nama Developer | Status
Finding Dataset | 2021-12-10 | 2021-10-15 | Yulisha Dian Cahyaningrum | Done | Keterangan
Analisis Dataset | 2021-12-15 | 19/10/2021 | Eka Yunia Primastuti | Done | On Going
Preprocessing Data Modul 1 - Part 1 | 23/10/2021 | 2021-10-25 | Eka Yunia Primastuti | Done | Waiting
Preprocessing Data Modul 1 - Part 2 | 2021-10-25 | 26/10/2021 | Yulisha Dian Cahyaningrum | Done | Done
Modelling Data menggunakan CNN Modul 1 - Part 1 | 2021-10-25 | 27/10/2021 | Eka Yunia Primastuti | Done
Evaluasi model CNN 1 | 2021-10-25 | 27/10/2021 | Eka Yunia Primastuti | Done
Modelling Data menggunakan CNN Modul 1 - Part 2 | 2021-10-25 | 27/10/2021 | Yulisha Dian Cahyaningrum | Done
Evaluasi model CNN 2 | 2021-10-25 | 27/10/2021 | Yulisha Dian Cahyaningrum | Done
Prepocessing Data Modul 2 | 2021-11-07 | 2021-11-07 | Collaborasi | Done
Modelling Data Maxpool Oversampling Modul 2 - Part 1 | 2021-11-07 | 2021-11-07 | Yulisha Dian Cahyaningrum | Done
Modelling Data Average Oversampling Modul 2 - Part 2 | 2021-11-08 | 2021-11-08 | Eka Yunia Primastuti | Done
Prepocessing Data Modul 3 | 2021-11-22 | 2021-11-22 | Collaborasi | Done
Modelling Data Maxpool HParams Modul 3 - Part 1 | 2021-11-22 | 2021-11-24 | Yulisha Dian Cahyaningrum | Done
Modelling Data Average HParams Modul 3 - Part 2 | 2021-11-24 | 2021-11-26 | Eka Yunia Primastuti | Done
Modelling menggunakan VGG19 | 2021-12-05 | 2021-12-07 | Eka Yunia Primastuti | Done
Modelling menggunakan VGG19 | 2021-12-07 | 2021-12-09 | Yulisha Dian Cahyaningrum | Done
Modelling menggunakan InceptionV3 | 2021-12-19 | 2021-12-21 | Eka Yunia Primastuti | Done
Modelling menggunakan VGG19 | 2021-12-21 | 2021-12-23 | Yulisha Dian Cahyaningrum | Done
Development Front-End-Web | 2021-12-30 | 2021-12-01 | Collaborasi | Done
Configurasi Flask | 2021-12-30 | 2021-12-01 | Collaborasi | Done
Development Back-End-Web | 2021-12-30 | 2021-12-01 | Collaborasi | Done
Deployment | 2021-12-30 | 2021-12-01 | Collaborasi | Done