## Sheet1
Job Desk
Task | Tanggal Mulai | Tanggal Selesai | Nama Developer | Status
Finding Dataset | 2021-12-10 | 19/10/2021 | Eka Yunia & Yulisha Dian | Done
Preprocessing Data | 23/10/2021 | 26/10/2021 | Yulisha Dian | Done
Training | 23/10/2021 | 27/10/2021 | Eka Yunia & Yulisha Dian | On Going
Modelling | 23/10/2021 | 27/10/2021 | Eka Yunia | On Going
Model Inference
Model Evaluation
Prediksi Data
Testing